## Slide 1
Website Update
Project Introduction
Yujia Yao, Data Scientist | Maclear | May 2026
Confidential — Internal Use

## Slide 2
Why This Project Matters
Business problem and strategic value
Maclear | Website Update | Confidential
• Current website contains outdated and inaccurate content with no reliable update process
• Manual updates risk inconsistency, formatting damage, and unauthorized content changes
• A reusable update pipeline will improve SEO, increase customer engagement, and reduce operational risk
• Prevents outdated or unsupported content from remaining on the live site
• Supports Maclear's commitment to precision, transparency, and controlled delivery

## Slide 3
Scope and Deliverables
What is — and is not — included
Maclear | Website Update | Confidential
IN SCOPE
OUT OF SCOPE
• Review current website content — identify outdated sections
• Confirm approved replacement content with client
• Build reusable content-update pipeline
• Test pipeline in staging environment before any live change
• Apply approved updates to live website
• Document pipeline for future update cycles
• Creating original content (LLM cannot generate beyond approved source)
• New website functionality or features
• Website redesign or restyling
• Modifying content that is already approved
• Unrelated technical changes to the website platform

## Slide 4
What Success Looks Like
Acceptance criteria
Maclear | Website Update | Confidential
✔ Pipeline updates content accurately — zero hallucinated or unsupported output
✔ Approved existing content is fully preserved after every update
✔ Formatting and page structure are intact post-update
✔ No update reaches the live site without explicit written approval
✔ Pipeline is reusable and documented for future update cycles
Mandatory constraint: LLM must not generate new content beyond the approved source material

## Slide 5
Project Timeline
Apr 1 – Jun 1, 2026 | Estimated schedule
Maclear | Website Update | Confidential
Phase 1: Initiation
Apr 1–7
Phase 2: Content Audit
Apr 2–6
Phase 3: Pipeline Development
Apr 8–24
Phase 4: Testing & QA
Apr 27–May 1
Phase 5: Review & Approval
May 4–8
Phase 6: Deployment
May 11–14
Phase 7: Docs & Closeout
Apr 27–May 15
TODAY May 7
Start: Apr 1, 2026 | Prototype target: Apr 24 | Approval gate: May 8 | Live update: May 12 | Close: May 15 (Hard deadline: Jun 1)

## Slide 6
Key Milestones
Four critical checkpoints
Maclear | Website Update | Confidential
Milestone
Target Date
Owner
Status
Prototype (pipeline v1) released
Apr 24, 2026
Yujia Yao
At risk — confirm
Approval to deploy
May 8, 2026
Jesus Calderon
Not started
Live website updated
May 12, 2026
Yujia Yao
Not started
Project complete (hard deadline)
Jun 1, 2026
Jesus Calderon
Not started
M1 is flagged At risk: the Apr 24 target has passed as of today (May 7). Confirm actual pipeline status before re-baselining.

## Slide 7
Workstreams and Task Summary
7 phases | 16 tasks | single executor
Maclear | Website Update | Confidential
Phase
Key Tasks
Est. Duration
Status
1. Initiation
Kickoff, access setup, API permissions, content collection
~1 week
Confirm status
2. Content Audit
Review current website; identify outdated sections
3 days
Confirm status
3. Pipeline Dev
Architecture design, pipeline build, staging environment setup
~3 weeks
Confirm status
4. Testing & QA
Staging tests: accuracy, formatting, approval workflow
1 week
Confirm status
5. Review & Approval
Owner review of proposed changes + written approval gate
1 week
Not started
6. Deployment
Live update + post-deployment verification
4 days
Not started
7. Docs & Closeout
Pipeline documentation + final sign-off
3 days
Not started
Total tasks: 16 + 4 milestones | Single resource: Yujia Yao (full-time Mon–Fri)

## Slide 8
Roles and Responsibilities
Who does what
Maclear | Website Update | Confidential
Role
Person / Team
Responsibilities
Availability
Project Lead / Developer
Yujia Yao
All execution: audit, build, test, deploy, document
Full-time Mon–Fri
Decision-Maker / Approver
Jesus Calderon
Scope, budget, schedule; two hard approval gates
TBD — confirm
Content Provider
Maclear / Alco Insights
Deliver approved source content; confirm content package
External — TBD
AI/API Services
OpenAI / Claude
LLM component of the content-update pipeline
Subject to license
Final Approver
TBD — Not provided
Approve final deliverables
TBD — confirm
Risk: Yujia Yao is the sole executor. Any absence halts all project work. No current mitigation.

## Slide 9
Key Risks and Mitigations
Top 5 risks — all rated High severity
Maclear | Website Update | Confidential
Risk
Prob.
Impact
Mitigation
Client content not delivered on time
High
High
Confirm delivery date now; escalate if delayed
LLM generates unsupported content
Medium
High
LLM reformats only — never generates new content
Approved content overwritten by pipeline bug
Medium
High
Pre/post diff review + approval gate before live deploy
Approval gate delayed (Jesus Calderon)
Medium
High
Set 2-day response expectation; escalate early
Single-resource risk — Yujia Yao only executor
Medium
High
Flag to Jesus Calderon — no current mitigation

## Slide 10
Open Decisions and Confirmations Needed
Items blocking schedule re-baseline
Maclear | Website Update | Confidential
HIGH PRIORITY — must answer this week
⚠ Actual task status as of today (May 7) — has the prototype been delivered?
⚠ Who is the final deliverable approver? (left blank in questionnaire)
⚠ Has approved source content been received from Maclear / Alco Insights?
⚠ Are website admin access and AI/API access confirmed?
MEDIUM PRIORITY — needed before pipeline build is finalized
● Should automatic update functionality be in scope?
● Should style/design updates be included?
● How much automation vs. manual approval should the pipeline require?
● Confirmed budget ceiling (range given: $50–$5,000)

## Slide 11
Recommended Next Steps
Actions for the week of May 7, 2026
Maclear | Website Update | Confidential
1
Confirm current task status with Yujia Yao — update progress on all early tasks immediately
This week
2
Confirm final deliverable approver with Jesus Calderon
This week
3
Confirm approved source content received from Maclear / Alco Insights
This week
4
Confirm website access and AI/API access are secured
This week
5
Answer three open scope decisions: automation, design updates, approval flow
This week
6
Re-baseline the project schedule after confirming actual task status
After steps 1–5
7
Proceed to Gantt chart execution tracking with updated progress
After step 6